## Zach
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/25-2/1) | 6 | 5 | 1 | 0 - started exploring ruby 6 - setting up windows VM | 2 | [5 empty] | 3 | 5 - SPPP work | 6
2 (2/2-2/8) | 5 | 4 | 1 | 0 - Ruby lookover 5 - SPPP Documentation | 1 |  |  |  |  | 3
3 (2/9-2/15) | 3 | 2 | 1 | 0 - Ruby example | 2 | [6 empty] | 3 - User list creation | 6
4 (2/9-2/15) | 4 | 3 | 1 | 0 - Environment setup | 3
5 (2/16-2/22) | 3 | 3 |  | 0 - Ruby walk through | 3 | [6 empty] | 0 - User list testing and verification 5 - Documentation for iteration 1 | 9
6 (2/23-3/1) | 8 | 7 | 1 | 5 - Documentation updates 6 - Git repo reorginization 1 - Requirement refinement |  | 3 |  |  |  | 3 | 1 | 3 - Iteration 2 tasks | 10
7 (3/2-3/15) | 12 | 11 | 1 | 2 - Groups design 0 - Ruby CRUD example 3 - Groups work | 2 |  | 3 | 6 |  |  |  | 3 - more group implementation | 10
8 (3/16-3/22) | 7 | 6 | 1 | 3 - Groups page work |  |  |  | 5 |  |  |  | 3 - Finish up groups page 5 - Documentation for iteration 2 | 12
9 (3/23-3/29) | 16 | 15 | 1 | 3 - Groups page work 5 - Documentation updates |  |  |  | 13 |  | 2 |  | 3 - Start work for iteration 3 | 8
10 (3/30-4/5) | 5 | 4 | 1 | 3 - Groups page work |  |  |  | 4
11 (4/6-4/12) | 3 | 2 | 1 | 3 - Groups page updating |  |  |  | 2
12 (4/13-4/19) | 8 | 7 | 1 | 3 - CSS updating |  |  |  | 7 |  |  |  | 5 - documentation for iteration 3
13 (4/20-4/26) | 5 | 4 | 1 | 5 - Documentation for iteration 3 | [5 empty] | 4

## Yiannis
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/25-2/1) | 5 | 4 | 1 | 6 - Setting up environment 0 - exploring jenkings 0 - signing up for pivotal, exploring pivotal and other miscellaneous tasks | 2 | [5 empty] | 2
2 (2/2-2/8) | 4 | 3 | 1 | 0 - ruby tutorials 1 - setting up pivotal | 2 | 1
3 (2/9-2/15) | 2 | 2 | 0 | 0 - ruby tutorials 6 - setup environment | 1 | [5 empty] | 1
4 (2/16-2/23) | 7 | 6 | 1 | 0 - ruby tutorials 1 - requirement analysis 6 - environment setup | 3 | 1 |  |  |  |  | 2
5 (2/24-3/1) | 26 | 25 | 1 | 2/3 - SW development (user lists/item creation, deletion, modification) 1 - Pivotal Tracker updating 4 - ad hoc testing |  | 1 | 4 | 16 | 4
6/7 (3/2-3/15) | 1 | 0 | 1
8 (3/16-/22) | 3 | 2 | 1 | 2/3 - SW dev 4 - ad hoc testing |  |  |  | 1 | 1
8 (3/13-/29) | 5 | 4 | 1 | 2/3 - SW dev 4 - ad hoc testing |  |  |  | 3 | 1
10 (3/30-4/5) | 3 | 2 | 1 | 2/3- SW dev 4 - ad hoc testing |  |  | 1 | 2 | 1
11 (4/6-4/12) | 5 | 5 | 0 | 2/3 - SW dev (flash messages) 4 - ad hoc testing |  |  | 1 | 2 | 2
12 (4/13-4/19) | 15 | 14 | 1 | 2/3 - Fixed Flash messages. They are now visible. Error checking added for user input into new list, list item and group creation. All possible permutations of wrong data covered with appropriate message informing which fields may be invalid. Added images to view of list items. For Images, error checking occurs only if the field is not empty since it is optional. If it is not empty error checking consists of making sure the image URL has substrings [ (".jpg" ¦¦ ".png" ¦¦ ".apng") && ("http://" ¦¦ "https://") ]. There may be a better way to do this so if you know of one feel free to implement that instead. Some sort of magic ruby function i presume may work for this. Made "purchased" status visible to appropriate parties. Took away non-onwer's ability in group to add item, delete list and delete item. Gave non-owner in group ability to mark items as purchased. Ran some ad hoc tests on what i thought were all possible scenarios for all the code i changed. Merged in Master and groups_continued branch to this branch. 4 - ad hoc testing |  | 1 | 3 | 9 | 2
13 (4/20-4/26) | 6 | 5 | 1 | 1- requirements cleanup and addition to slides 5 - end of project cleanup |  | 3 |  |  |  | 2

## Duncan
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25/218 - 1/31/18 | 7 | 6 | 1 | 1/5 - Project requirement analysis, and organization for team meeting. 3 - Initial project setup, github setup |  | 1 |  | 3 |  | 2 |  | Fill out relevant SPPP sections, prepare presentation, begin work on homepage | 6-8 hrs
2/1/18 - 2/7/2018 | 9 | 8 | 1 | 5 - SPPP Documentation, 3 - Rails setup, initial homepage setup, 0 - Rails Tutorials, 2 - Presentation creation/setup | 1 |  | 1 | 4 |  | 2 |  | Iteration 1: Homepage design, User model design, Team Management | 8
2/8/2015-2/14/2018 | 7 | 6 | 1 | 0- Rails framework review 5 - organizing team processes 3 - Implementing controllers/homepage 2 - designing homepage | 2 |  | 2 | 1 |  | 1 |  | Homepage/controllers initial version | 8
2/15/18 - 2/21/18 | 8 | 7.5 | 1 | 1 - Pivotal tracker recording 2 - Wireframes 3 - Creating homepage/controllers 5 - managing teammates work |  | 1.5 | 1 | 4 |  | 1 |  | Homepage v2, user page css/redo | 10
2/22/18 - 2/28/18 | 17 | 16 | 1 | 0 - Rails training 1- Adding new pivotal tracker items, updating exists 2 - Homepage redesign spec 3 - Homepage/controller implementation 5 - Pull request reviewing/team management | 1 | 1 | 1 | 8 |  | 5
3/1/18-3/14/18 | 14.5 | 12.5 | 2 | 0 - CSS styling 1 - Pivotal tracker submission and prioritzing iteration 2 2 - Wireframe of Groups page 3 - Homepage CSS, User model refactor 5 - Team meetings, meeting planning | 2 | 2 | 1.5 | 5 |  | 2
3/15 - 3/21 | 15 | 14 | 1 | 3 - User, List page/controller rewrite 5 - meetings/organizing |  |  |  | 14 |  | 1
3/22 - 3/28 | 5 | 4 | 1 | 3 - List item rewrite 5 - Iteration 3 planning |  | 1 |  | 3
3/29 - 4/4 | 11 | 10 | 1 | 3 - CSS Redesign 5 - Team managment |  |  |  | 8 |  | 2
4/5 - 4/11 | 8 | 7 | 1 | 3 - CSS Redesign 5 - Presentation planning |  |  |  | 6 |  | 1
4/12 - 4/18 | 9 | 8 | 1 | 3 - CSS Redesign 5 - Presentation planning/organizing, reviewing pull requests |  |  |  | 4 |  | 4
4/19 - 4/25 | 6 | 5 | 1 | 5 - Presentation preparation, last pull request reviews | [5 empty] | 5

## Ben
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25/218 - 1/31/18 | 5 | 4 | 1 | Learning RoR basics and configuring environment | 4 | [6 empty] | Work on SPPP | 4
2/1/18 - 2/7/2018 | 6 | 5 | 1 | Continuing to learn RoR, working on SPPP, learning SQL Server basics | 5 | [6 empty] | Create authentication system and create a simple AWS deployment demo
2/8/18 - 2/14/18 | 9 | 8 | 1 | Investigated Google Authentication API and made a demo app and whitepaper | 4 |  | 2 | 2 |  |  |  | Finish and merge authentication code. Set up dev and production environments in Ruby to accomodate not being able to use Google auth in local environment. | 8 hours or more
2/15/18 - 2/21/18 | 14 | 13 | 1 | 0 - Read RoR eBook 1 - Adding requirements to pivotal tracker 3 - Created login branch | 8 | 1 |  | 4 |  |  |  | Finish auth and merge it | 8
2/22/18 - 2/28/18 | 11 | 10 | 1 | 3 - Scrapped login branch based on team feedback and created authentication branch with a controller and helper to add log in/sessions/log out 4 - Created unit and integration tests for session controller, helper, user controller 6 - configured SQL Server environment |  |  |  | 6 | 3 |  | 1 | Add refinement and more testing to authentication code | 6
3/1/18-3/14/18 | 5 | 4 | 1 | 0 - learn about RSpec 2 - plan refactor, remaining authentication features, production environment. | 2 |  | 2
3/15/18-3/21/18 | 8 | 7 | 1 | 0 - more learning of RSpec 3 - refactored and improved hashing, strengthened password requirements | 3 |  |  | 4 |  |  |  | Create session persistence and write tests | 6
3/22/18-3/28/18 | 8 | 7 | 1 | 3 - Implemented session persistence and other misc items. Finished my 'improve_authentication' branch and merged it. 4 - Modify existing Minitest tests to RSpec format and get them all passing |  |  |  | 4 | 3 |  |  | AWS deployment | 8
3/29/18 - 4/4/18 | 6 | 5 | 1 | 0 - Learn about Rails security features on OWASP, survey security testing gems | 4
4/5/18 - 4/11/18 | 4 | 3 | 1 | 0 - survey deployment options | 3
4/12/18 - 4/18/18 | 11 | 10 | 1 | 3- Configure AWS production environment |  |  |  | 10
4/19/18 - 4/25/18 | 9 | 8 | 1 | 3 - finish AWS configuration 4 - fix authentication bugs and add relevant tests 5 - Updated SPPP Configuration Management section |  |  |  | 4 | 3 | 1

## Ed
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25/18 - 1/31/18 | 7 | 6 | 1 | 0 - Intro Ruby, Rails, AWS | 6 | [6 empty] | 0 - Rails, Active Record 5 - SPPP | 8
2/1/18 - 2/7/18 | 9 | 8 | 1 | 0 - Active Record adapters/gems, authentication 3 - Added gems for DB access, authentication 5 - SPPP QA Plan | 1 |  |  | 1 |  | 6 |  | 0 - MVC 2 - DB schema, models 3- DB schema, models | 12
2/8/18 - 2/14/18 | 9 | 8 | 1 | 0 - Active Record 2 - Initial DB schema 3 - Begin implementing models based on schema | 4 |  | 2 | 2 |  |  |  | 0 - Active Record, Migrations 3- Implement initial schema as models/tables | 10
2/8/18 - 2/21/18 | 16 | 15 | 1 | 0 - Active Record, Migrations, Unit Testing 2 - Models for User, Group, List, ListItem 3 - Models for User, Group, List, ListItem 4 - Unit tests for CRUD on models 5 - White paper for Windows environment variables | 2 |  | 2 | 8 | 2 | 1 |  | 4 - expand model unit tests 5 - SDP, STP | 12
2/22/18 - 2/28/18 | 27 | 26 | 1 | 0 - RSpec, SimpleCov 3 - Unit test updates, test statistics, assisting other implementation activities 4 - Test reporting, system tests for I1 5 - SDD, STP | 2 |  |  | 4 | 8 | 12 |  | 2 - additional Model refactoring 3 - convert tests to spec, add additional test coverage 4 - add system tests for Iteration 2 functionality | 8
3/1/18 - 3/7/18 | 6 | 5 | 1 | 0 - RSpec, SimpleCov 3 - merge iteration 1 changes to master branch | 2 |  |  | 3 |  |  |  | 0 - RSpec, SimpleCov 3 - Pilot transitioning testing framework to RSpec | 8
3/8/18 - 3/14/18 | 9 | 8 | 1 | 0 - RSpec, SimpleCov 3 - Transition testing framework to RSpec | 2 |  |  | 6 |  |  |  | 2 - Group member recommendations 3 - Group member recommendations 5 - Update SDD with group member recommendation algorithm | 12
3/15/18 - 3/21/18 | 11 | 10 | 1 | 0 - Parallelism in Ruby 2 - suggestion cache 3 - Implement user suggestion cache for groups 4 - RSpec tests for user suggestion cache | 2 |  | 1 | 4 | 3 |  |  | 3 - Assist with group-related functionality 4 - Update/execute functional test 5 - Update SDD/STP | 16
3/22/18 - 3/28/18 | 12.5 | 12 | 0.5 | 3 - Merging dev branches to test branch, bug fixes, etc. 4 - Complete iteration 2 testing reports, functional tests 5 - Update SDP, STP, PivotalTracker for iteration 2 |  |  |  | 4 | 4 | 4 |  | 3 - Clean up existing functionality; code analysis compliance 4 - Code coverage improvements, acceptance test drafting | 8
3/29/18 - 4/4/18 | 9.5 | 9 | 0.5 | 0 - Rails views 3 - Wire up user suggestion to UI; groups view/controller refactoring | 1 |  |  | 8 |  |  |  | 3 - Allow user addition to groups by email address 4 - additional unit testing coverage | 8
4/5/18 - 4/11/18 | 8.5 | 8 | 0.5 | 3 - Allow for users to be added directly via email or from user suggestion 4 - Additional unit test creation |  |  |  | 6 | 2 |  |  | 3 - Start getting code ready for final merge 4 - ad hoc testing 6 - assist with AWS deployment (particularly database) | 8
4/12/18 - 4/18/18 | 7.5 | 7 | 0.5 | 3 - Refactoring list item to support site and image URLs, code cleanup 4 - Functional test case updates 6 - Support/troubleshooting for AWS deployment |  |  |  | 4 | 2 |  | 1 | 3 - merge iteration 3 code to master, final cleanup 4 - complete functional testing for iteration 3 5 - Update SDD, STP for iteration 3 work | 8
4/19/18 - 4/26/18 | 24 | 23 | 1 | 3 - Code cleanup, miscellaneous bug fixing 4 - testing for iteration 3 5 - Update SDP, STP, PivotalTracker, Presentation for iteration 3 6 - Presentation prep |  |  |  | 6 | 12 | 3 | 2 | 6 - finalize submission for term project | 1

## Midterm Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | Proposal and Planning Document (SPPP) | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Ben | Added requirements to Pivotal tracker, updated relevant tasks/stories as I worked | Created configuration management plan section, will add more in iteration 2 when I finish configuring our deployment environment |  |  |  | Created a demo Ruby app for Google Auth which we ended up abandoning. Then wrote all the of authentication code. Created login branch which I ended up abandoning based on team feedback. Created authentication branch with login and signup views, the sessions controller, the sessions helper, most of the users controller, changes to user model, unit and integration tests for these items) | Wrote integration test for controllers (user and session controllers) and unit tests for sessions helper. |  | Active in meetings and Slack channel
Duncan | I created 4 requirements on Pivotal tracker and updated those relevant to me as I worked | I wrote the Overivew and Related work sections of the SPPP, as well as helped review other parts | I wrote the Design Patterns section |  | I presented for Iteration 0 and created half the slides | I created the application framework, the homepage, the shell of all other pages. I was in charge of styling all pages and reviewed pull requests for users/authentication | I created a few unit tests for the homepage | I set up our github repo | I ran the team meetings, created agendas, and helped organize what was worked on. Worked as a resource for others if they needed help with the stories.
Ed | Entered 3 requirements, 5 defects into PivotalTracker | Wrote QA Plan | Wrote all but Design Patterns section, created DB schema, UML | Wrote STD and supporting documentation (Test cases, results) | Presented for iteration 1, provided diagrams for both iteration 0 and iteration 1 presentations | Added model framework, provided feedback/assistance on implementations for users/lists and authentication | Implemented unit tests for models. Wrote and executed functional system tests. | Database configuration for development, test, production environments | Facilitated troubleshooting/implementation efforts for various activities, white paper creation, active in Slack channel
Yiannis | Setup Pivotal Tracker account and added several user stories. Helped organized stories into current iteration and icebox and updated user stories as i worked on them | Organized and wrote user stories in their proper format |  |  | Presented for iteration 1 | Learned basic Rbuy skills as well as web development and sql database. Coded ability for user to create, modify and delete lists. Also coded ability for users to add and delete items to lists. Merged code into demo branch for iteration 1 demo. | Did not create any unit tests. Just did ad hoc testing as i developed | merged major branches for iteration 1 demo | Took meeting notes once and attended meetings
Zach | I was responsible for 3 requirements on pivotaltracker. One of which got merged into a larger story. | Responsible for the Management Plan and the Risk Table |  |  | Presented for iteration 0 and organized the powerpoint for iteration 1 | Spent time getting up to speed on Ruby. Did reorganize the files on github and committed all of the documents required for each iteration | Have checked out several branches with an open pull request to make sure it ran in my environment and the code did what was claimed |  | Have been responsible for taking meeting minutes and been active in the slack channel.

## Final Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Ben | Implemented 2 stories and fixed 2 bugs. |  |  | Presented for iterations 2 and 3. Discussed security features and deployment process. | Created the session helper and session controller and authentication related sections of the user model and user controller and relevant tests and DB migrations. | Unit tests for my methods. Used Brakeman to assess configuration of Rails security features. | Created AWS production environment and deployment script. Extensive troubleshooting on EC2 instances to get dependencies to build. Created RDS database and fixed firewall and initialization issues. | Active in Slack channel and weekly meetings.
Duncan | Implemented 3 stories, fixed 2 bugs, completed 2 chores | I wrote the design patterns section |  | Presented iteration 0 and organized final presentation, did introduction, implementation sections of final presentation | Wrote almost all css and site design, created homepage, rewrote user, list and list item controllers/views, assisted others in creating pages/adding other functionality | Wrote some unit tests for implemented controllers | Set up github environment and reviewed almost all pull requests | Organized all weekly meetings and agendas, delgated and organized what work everyone took on, reviewed pull requests, ensured all requirements and submissions hit for every iteration
Ed | Entered 3 requirements, 5 defects into PivotalTracker. Managed defect tracking process in PivotalTracker | Wrote all but Design Patterns section, created DB schema, UML | Wrote STD and supporting documentation (Test cases, results) | Presented for iteration 1 and 3, provided diagrams for both all iteration presentations | Added maintained model framework, Added user suggestion support for group membership. Assisted in refactoring, bug fixing, and addressing issues from static code analysis | Defined and maintained unit testing framework. Wrote unit tests for models, other resources. Performed integration testing at the end of each iteration. Performed system testing (writing/execution) of test cases at the end of each iteration | Database configuration for development, test, production environments; Troubleshooting for AWS deployment incorporating remote SQL database | Facilitated troubleshooting/implementation efforts for various activities, white paper creation, active in Slack channel
Yiannis | Implemetned 3 stories and a couple bug fixes in last iteration. helped manage pivotal tracker near end of iteration 3 |  |  | Presented for iteration 1 and 3. Helped create iteration 1 and 3 presentations | Learned Ruby in the beginning. Helped organize branches for iteration 1 and contributed heavily to codebase in iterations 1 and 3 in several branches spanning many areas of the code. Mainly focused on CRUD ability for lists and list items as well as some group functionality regarding CRUD and item property visibility. | Mostly contributed to testing in an ad hoc manner. Tested code as i wrote and implemented it. | Setup pivotal tracker at beginning of project and helped maintain throughout | Attended weekly meetings and checked slack regularly.
Zach | Implemented 2 stories and a bug fix. |  |  | Presented Iteration 2 and 3. Showed Group updates as well as our work cycle overview | Started out the semester putting in time learning Ruby. Once I felt my skills were adequate, I implemented the Groups functionality. Mainly working on the groups_controller and groups view. Also was responsible for uploading documentation to github. | Made sure to test my code to the best of my abilities during my development | As the only developer on MacOS, I was able to download and configure my own work environment for windows to fit in with the team and make development easier for the group as a whole | Active in weekly meetings, used slack as means of communicating problems and asking questions. Also was responsible for taking meeting notes from time to time.