## Sheet1
Risk Title | Description | Estimated likelihood of occurrence (1-5 or H/M/L) | Estimated Impact (1-5 or H/M/L) | Estimated retirement Cost | priority | responsible engineer | target completion date | detailed plan
Team Member Dropping/lagging | Team member either drops the course or is unresponsive | 2 | 5 | 2 |  |  |  | Reassign that teammates tasks if they drop the class. Have a meeting with a teammate who isn't pulling their load. Try to get the teammate motivated to contribute to the group.
Knowledge | Team members have a tough time getting up to speed with ruby on rails development | 4 | 5 | 4 |  |  |  | Have a more experienced group memeber set up a lecture to bring the team up to speed. Or provide the lacking team members with helpful tutorials that they can follow.
UI Development | No team members have a real knowledge of UI/javascript programming | 5 | 3 | 4 |  |  |  | A team member will take on the part of developing the front end. If that team member is having trouble, then the rest of the team will get together to contribute where they can so that the project has a good UI.
Configuration | Some part of the project (DB, UI, Ruby) is not working properly. | 5 | 5 | 4 |  |  |  | The key would be to have all team members swarm the issue and work to solve the configuration issue. The project doesn't work without each major component.
Merge Conflicts | When a new feature is being added, a merge conflict may occur | 5 | 2 | 1 |  |  |  | The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Developer Environment | The developer environment may be difficult to setup and to get working smoothly | 4 | 3 | 2 |  |  |  | Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.
Bugs | When testing, bugs may appear and cause functionality issues | 5 | (bug dependent) | (bug dependent) |  |  |  | Pivotal Tracker will be used to keep track of issues and developers will get assigned bugs based on the sections of the code that they worked on.